## Sheet1
Project Plan
Week 7/28Oct | First meeting with supervisor, Start working on plan.
Week8/4Nov | 1. Plan Finished for semester 1 and have brief overview of semester 2 plan.
2. took book from library about Raspberry Pi projects and have little overview
3. Download Raspbian and ask a friend to bring Rpi to college in next class.
Week9/11Nov | 1. Finalize plan after supervisor meeting and got Rpi from college (supervisor)
2. Draft of first Chapeter, Table of content(at least will have idea about semester 1 submission )
3. Read and learn how to configure motion sensor on Rpi using Rpi guide book
Week10/18Nov | 1. Must install Raspbian in Raspberry Pi and try to get motion sensor from college and try to use that with Rpi using knowledge gain from Rpi guide
2. Also need to finalize camera module that I will be using and order that ASAP, must finalize the project architecture that can be included to chapter 1 draft.
3. Start working on project proposal according to table of content(first need to focus on introduction, problem, problem solution etc)
4. Semester 2 timeline in detail as per supervisor valuable suggestion.
Week11/25Nov | 1. Motion sensor should be working fine at this stage (if could not configure previously, must need to done the the end of this week)
2. After architecture design identify programming language that will be useful for project and start learning that.
3. Add technologies going to use in project(their discription, working and how that technology will help me in my project).
Week12/2Dec | 1. Read more related projects and compare with work done by me, and if some thing more efficient is found try to append that in project proposal.
2. Using Rpi guide book learn how to access camera module and how to make picture and videos with it.
3. learn python basics as it will be needed to configure Camera module.
Week13/9Dec | 1. Finalize first deliverable for submission as submission date will be by the end of this week expectedly
2. Make sure to cite Refrences used in project and cite that properly and also label images used in document if not done yet.
3. Test camera module if receive by this week and add documentation of experiment in Proposal draft.
Week14/16Dec | 1. proof reading of Deliverable 1 before submission
2019-12-21 | Exam period
until | Exam period
2020-01-24 | Exam period
Holidays until 16Feb | No extra work require during this time as I will be out of country for some time, but if any task missing from semester 1 should be completed in this time.
Semester 2 Starts | Timeline is not define yet, but few key tasks must need to do are specified below:-
Camera module and its testing with Rpi, configure both camera and motion sensor work together
Front end interface
Diagrams, (Use case, sequence etc )
Experiments with detail
Final prototype (final document ) presentation, video demonstration for external examiner etc.
Week1/17Feb | 1. If not tested the Camera module test that in this week.
2. Make Rpi OwnCLoud enabled and test it by storing data in Rpi and access it on other device.
Week2/24Feb | 1. Test both sensor and camera module together and make camera able to take pic/video when motion occur.
2. If not successful in capturing video when motion occur then do some troubleshoot research and make a report what happen and why is happening.
Week3/2Mar | 1. Once successful in capturing video when motion occur, test that at different times and make it to store videos with different names i.ee (name videos with Time.)
2. Also Access storage data on some other device using OwnCloud which must need to be tested and enabled on Rpi before this week as already specified in earlier weeks task..
Week4/9Mar | 1. Start writing final report, Document the experiments.
2. Add external hard drive to Rpi and enable OwnCloud service on it.
Week5/16Mar | 1. Start working on Daigrams (Methodology), i.e use Case diagram, Activity Diagram, Sequence Diagram.
2. Core task need to be done before this week as specified already for previous weeks, research on how to make Rpi to send somew sort of notification if any motion occur.
Week6/23Mar | 1. Do practical to make Rpi able to send notification if motion occur (make some simple app where user can login and see notifications)
2. Write the final prototype made so far, (if become successful in sending notifications it can be added later on the final prototype document.)
Week7/30Mar | 1. Focus on Final document and its enhancement and also add researech done in order to sent notification message.
2. This week also do some work on making Rpi able to sent noftifications /messages (it will enhance the project functionality).
Week8/6Apr | Feedback for semester1 draft will be received by this time, So try to make changes in final document if somethings missiing.
Week9/13Apr | Near end of semester there may be pressure of other subjects assignments, so practical work should be done before April and leave this month to work on Documentation and experiments.
Week10/20Apr | Finalize the Document and Show working model to supervisor and document to seek advices and implementations if needed.
Week11/27Apr | If any suggestions from supervisor change and add that functionalities to project final articraft and also Make a presentation file for final presentation.
Week12/4May | End of Semester. Submission expected this week. Read the finalize document to find mistakes if any and try to make it Efficient. Also need to record video if asked.