## Sheet1
Project Plan
Week 7/28Oct | First meeting with supervisor, Start working on plan.
Week8/4Nov | 1. Plan Finished for semester 1 and have brief overview of semester 2 plan.
2. took book from library about Raspberry Pi projects and have little overview
3. Download Raspbian and ask a friend to bring Rpi to college in next class.
Week9/11Nov | 1. Finalize plan after supervisor meeting and got Rpi from college (supervisor)
2. Draft of first Chapeter, Table of content(at least will have idea about semester 1 submission )
3.Read thoruoghly previous year projects and compare with work done by me, and if some thing more efficient is found try to append that in project proposal.
4. Read and learn how to configure motion sensor and camera module on Rpi using books
Week10/18Nov | 1. Must install Raspbian in Raspberry Pi and try to get motion sensor from college and try to use that with Rpi using knowledge gain from Rpi guide
2. Also need to finalize camera module that I will be using and order that ASAP, must finalize the project architecture that can be included to chapter 1 draft.
3. Start working on project proposal according to table of content(first need to focus on introduction, problem, problem solution etc)
4. Left empty for suoervisor suggestion
Week11/25Nov | 1. Motion sensor should be working fine at this stage (if could not configure previously, must need to done the the end of this week)
2. After arcitecture design identify programming language that will be useful for project and start learning that.
3. If research done until this week document that (proper citation and harvard refrencing required)
4. Add technologies going to use in project(their discription, working and how that technology will help me in my project).
Week12/2Dec | 1. Read more related projects and compare with work done by me, and if some thing more efficient is found try to append that in project proposal.
2. Do some experiments with motion sensor. Test at different times and try to store logs of motion occur at different times by showing time at motion occur
3. Using Rpi guide book learn how to access camera module and how to make picture and videos with it.
4. Left empty for suoervisor suggestion
Week13/9Dec | 1. Finalize first deliverable for submission as submission date will be by the end of this week expectedly
2. Make sure to cite Refrences used in project and cite that properly and also label images used in document if not done yet.
3. proof reading of Deliverable 1 before submission
2019-12-16 | Exam period
until | Exam period
2020-01-24 | Exam period
Holidays until 16Feb | No extra work require during this time as I will be out of country for some time, but if any task missing from semester 1 should be completed in this time.
Semester 2 Starts | Timeline is not define yet, but few key tasks must need to do are specified below:-
Camera module and its testing with Rpi, configure both camera and motion sensor work together
Front end interface
Diagrams, (Use case, sequence etc )
Experiments with detail
Final prototype (final document ) presentatation, video demonstration for external examiner etc.